## Guidance Sheet
SAFETY IN DESIGN RISK REGISTER (PLEASE OPEN THIS DOCT IN FULL DESKTOP VERSION OF EXCEL - TO VIEW ALL GUIDANCE NOTES)
Project:
Project Number:
Project Design Stage:
Project Type:
Designer:
SID Review Date:
Completed By:
Checked By:
Approved By:
Revision:
RISKS ASSOCIATED WITH DESIGN ELEMENT | [7 empty] | DESIGN MITIGATION MEASURES AND RESIDUAL RISK
[5 empty] | INITIAL RISK | [6 empty] | RESIDUAL RISK
Hazard Number | Activity / Process | Hazard and Outcome Source of risk and cause / event. (Refer to Typical Hazard Prompts tab). | Stage of Work (Investigation, Construction, Operation, Commissioning, Maintenance, Demolition) | Persons Affected (Construction Staff, Maintenance Staff, Public) | Likelihood | Consequences | Initial Risk Level | Controls What Mitigations and Control Measures are already in place or have been added to the design to Reduce Risk? (Eliminate, Reduce, Inform, Control) | Further Controls What further mitigations and control measures could be considered to reduce the residual Hazards? | Barriers What are the barriers that may apply to implement these Further Controls. Why can't we do more? | Actions and Date What actions are needed to escalate and consult on the resolution of any Further Controls that have not been applied? | Likelihood | Consequences | Residual Risk Level | Information Flow For Residual Hazards (Pre-construction Stage Plan - P, Drawings - D, SID Report on Completion - R, O&M Documents - O) | Risk Owner (Designer - D, Constructor - C, Operator - Op, Owner - Ow) | Due Date Expected Date to Issue final SID Register | COMMENTS
1 | Access to maintain Pumpstation wet well pumps on wastewater scheme | Confined spaces entry to Hazardous area, resulting in asphyxiation and possible drowning | Maintenance | Maintenance Staff | 5 | 5 | Critical | Pumps set up on a guide rail system for removal via remote access by mobile crane / Hiab or Davit from above ground without need for entering the wet well. This is a common design practice that has been used before. An air extraction system has been included in the wet well design. Isolation valves to be used between compartments to isolate all flows before entry. | Man riding basket access to be provided in cover slab to enable safe access to the pumps in the event of emergency access to pump - following agreed confined spaces entry procedures and protocols. | None likely | Close out at next SID workshop / Ops review, August 2021 | 2 | 5 | High | D,R | Op | 2021-12-01
2
3
4
Add more lines above here if required
Note on D4: Add the name of the Watercare Project (eg Snells Beach WWTP Upgrade)
Note on D5: Add the Project number, usually the Consultants Internal Project number
Note on D6: Use drop-down menu to select Project Design Stage. Additional Project Design Stages can be added in the lookup tab (see below - Col N )
Note on D7: Use drop-down menu to select Project Type. Additional Project Types can be added in the lookups tab (see below - Col I)
Note on D8: Insert name of Design Consultancy or Design and Build Company
Note on D13: As this is a "live" document this needs to be updated each time there is an update (e.g. 1, 2, 3, 4)
Note on I17: Please use drop down menu to populate the Likelihood and Consequences column as per the Risk Matrix Table above. Do not type anything in Column K as this updates automatically.
Note on R17: Please use drop down menu to populate the Likelihood and Consequences column as per the Risk Matrix Table above. Do not type anything in Column T as this updates automatically. This is the final residual risk level after implementing all agreed controls.
Note on C19: Describe the type of activity / process to which the hazard applies.
Note on D19: Hazard - This is something that has the potential to cause harm (such as working in a confined space, or near live traffic or working at height etc) Potential outcome of hazard- eg Burns, Ashyxiation, Drowning, Falling from a height etc...
Note on E19: Additional stages can be added in the lookups tab (Col A). If multiple stages are applicable then multiple hazard lines should be added.
Note on G19: Additional affected parties can be added in the lookups tab (Col C). If multiple affected parties are applicable then multiple hazard lines should be added.
Note on N19: Potental Further Controls could be something such as adopting a detail that may not be a WSL standard but can offer added H&S benefits - (eg such as challenging manhole access in certain instances and providing a smaller rodding eye jetting point instead). Consideration of so far as is reasonably practicable (SFAIRP) principles shall apply. This can be left blank if nothing apparent.
Note on O19: Barriers that may apply to enable these further controls - could be that further approval may be required at an Ops meeting, SID Workshop or a meeting with WSL Standards champion. This can be left blank if no Further Controls item is included.
Note on P19: This column is included if a Further Controls measure has been included - to indicate what is required to close this out and a target date. A process for escalation may be reqd if agreement cannot be reached. This can be left blank if no Further Controls item is included.
Note on V19: This is the location where the the residual hazard details will be included. Additional destinations can be added in the lookups tab (Col E)
Note on W19: Additional Owners can be added in the lookups tab (Col G). Only one Risk Owner should be assigned.
Note on B20: The text in this row is an example of a typical hazard on a project. It is provided for guidance only.

## Example SID Risk Register
SAFETY IN DESIGN RISK REGISTER
Project: |  | Southern Redhills
Project Number: |  | 422522
Project Design Stage: |  | Detailed Design
Project Type: |  | Wastewater Network
Designer: |  | Andre Aban
SID Review Date: |  | 2021-10-13
Completed By: |  | Sarah Perera
Checked By: |  | Pat Corris
Approved By: |  | Peter Evans
Revision: |  | A
RISKS ASSOCIATED WITH DESIGN ELEMENT | [7 empty] | DESIGN MITIGATION MEASURES AND RESIDUAL RISK
[5 empty] | INITIAL RISK | [6 empty] | RESIDUAL RISK
Hazard Number | Activity / Process | Hazard incl outcome Source of risk and cause / event. (Refer to Typical Hazard Prompts tab). | Stage of Work (Investigation, Construction, Operation, Commissioning, Maintenance, Demolition) | Persons Affected (Construction Staff, Maintenance Staff, Public) | Likelihood | Consequences | Initial Risk Level | Controls What Mitigations and Control Measures are already in place or have been added to the design to Reduce Risk? (Eliminate, Reduce, Inform, Control) | Further Controls What further mitigations and control measures could be considered to reduce the residual Hazards? | Barriers What are the barriers that may apply to implement these Further Controls. Why can't we do more? | Actions and Date What actions are needed to escalate and consult on the resolution of any Further Controls that have not been applied? | Likelihood | Consequences | Residual Risk Level | Information Flow For Residual Hazards (Pre-construction Stage Plan - P, Drawings - D, SID Report on Completion - R, O&M Documents - O) | Risk Owner (Designer - D, Constructor - C, Operator - Op, Owner - Ow) | Due Date Expected Date to Issue final SID Register | COMMENTS
D-01 | Excavation. | Excavation collapse, falling from height | Construction | Construction Staff | 3 | 5 | Critical | Contractor/Watercare H&S procedures, provision of barriers/fencing, contractor is to use geotechnical parameters derived from ground investigation in their temporary works design. Construction is planned to be undertaken in summer. If ground conditions encountered are different to expected, the Contractor is to notify the Engineer. Install approved shoring in accordance with Watercare's requirements and the Excavation Safety Good Practice Guideline. | If construction is to be undertaken during wet periods or over winter, trenchless construction should be considered. Dewatering of trenches to be considered. | Cost - Due to short lengths of pipelines the cost would be significantly higher than open cut. | Review at Safety in Design Meeting. Ensure all parties are aware that if the construction period shifts into winter, trenchless construction should be considered. | 2 | 5 | High | P,D,R | C | 2021-11-01
D-02 | Maintenance activities on manholes. | Fall, slips and trips and falling from height resulting in injury/death. Confined space access to manholes. | Maintenance | Maintenance Staff | 3 | 5 | Critical | Minimise maintenance access through safety in design and design specification (material, reducing number of manholes, appropriate manhole size, access/egress etc.), confined space entry, maintenance to be competent and properly trained. Emergency exit plan is in place and familiarised with staff and followed. Assess network risks for unusual risk e.g. operational history of known H2S hotspots and or close proximity gas mains. Ensure Watercare and Worksafe guidelines are followed. | Install manhole safety grilles at all manholes to reduce the risk of falling into the manhole. | Agree with Watercare Operations team. | Discuss at Safety in Design Meeting. | 1 | 5 | High | R,O | Op | 2021-11-01
D-03 | Setup, Construction and Commissioning in close proximity to services | Service strike, uncharted services | Construction | Construction Staff | 3 | 4 | High | Obtain information from Before U Dig, Council GIS plans, minimum safe offset distances from existing services. Install Pipeline D before other services in the vicinity. All critical services will be located, marked out, and pot holed ahead of construction. Stand overs and close work permits to be arranged where necessary. |  |  |  | 1 | 4 | Low | P | C | 2021-11-01
D-04 | Site investigation hazards: driving, services strike, plant, weather, etc. | Injury to personnel and/or public | Construction | Construction Staff | 3 | 3 | Medium | MM travel on site training, driving to work training, Watercare H&S procedures, Contractor H&S procedures. |  |  |  | 1 | 3 | Low | P | C | 2021-11-01
D-05 | Unauthorised public access to work site (excavations, trenches, pits) - vehicle/foot traffic | Injury to personnel and/or public | Construction | Public | 3 | 3 | Medium | Traffic management plans, appropriate site clearance, excavation protection, and provision of fencing, barricades, signage, site security. |  |  |  | 1 | 3 | Low | P | C | 2021-11-01
D-06 | Biological - exposure to wastewater | Illness, infection, death to personnel/public | Maintenance | Maintenance Staff | 3 | 5 | Critical | Unlikely to be exposed to wastewater during the construction of this pipeline as it is a new asset and there are no live wastewater flows expected until the pipeline has been commissioned. During maintenance, appropriate training and PPE, Watercare/Contractor H&S procedures, tie-in procedures, flow diversion/over pumping/management procedures. Maintain good hygiene standards when working around sewer drain. Use appropriate disinfectant. Ensure worker facilities are adequately provided on site in accordance with Worksafe guidelines. Keep up to date with required inoculations as per Watercare specifications. Keep a register of staff that have been inoculated and regularly check that it is up to date. |  |  |  | 1 | 5 | High | R | C | 2021-11-01
D-07 | Working in proximity of roads/live site/moving plant | Struck by vehicle, struck by debris | Construction | Construction Staff | 2 | 5 | High | Appropriate PPE, Contractor H&S practice and procedures, traffic management plans, provision of fencing, barricades, excavation protection, signage. |  |  |  | 1 | 4 | Low | P | C | 2021-11-01
D-08 | Construction in close proximity to watercourses and/or flow paths | Flooding, engulfment, falling, drowning, damage to assets | Construction | Construction Staff | 2 | 3 | Medium | Contractor/Watercare H&S procedures, provision of barriers/fencing, locate assets outside of flow path, construction staging (summer/dry weather), PPE |  |  |  | 1 | 3 | Low | P | C | 2021-11-01
D-09 | Carrier Pipe Construction | Limited/constraint access may lead to personnel falling/injury/death | Construction | Construction Staff | 3 | 5 | Critical | Lift plans, consider construction methods and timing. |  |  |  | 2 | 4 | Medium | P | C | 2021-11-01
D-10 | Wastewater high/low flows | Peak flows causing flooding, sickness, odour, disturbance to public. Low flows causing septicity, odour, H2S, blocking, damage to assets | Maintenance | Maintenance Staff | 4 | 5 | Critical | Design assets to Watercare standards and meet critical requirements (self cleansing, capacity, velocity, retention time, ventilation) Confined space entry, PPE, gas detectors, etc. |  |  |  | 2 | 3 | Medium | P | Op | 2021-11-01
D-11 | Flooding/wastewater | Flood damage to site and assets, flooding-related slips causing injury, wastewater flooding damage to watercourse/environment | Maintenance | Maintenance Staff | 2 | 4 | Medium | Design assets to have sufficient capacity, sufficient freeboard during PWWF operation |  |  |  | 1 | 3 | Low | P | Op | 2021-11-01
D-12 | Public climbing/accessing carrier pipe | Fall, slips and trips and falling from height resulting in injury/death, damage to assets | Maintenance | Maintenance Staff | 3 | 5 | Critical | Fencing to be provided by Developer to prevent access to pipe. | Include barrier protection to prevent access. | Unknown interface with Developers design regarding this area. | Discuss at SiD meeting | 1 | 4 | Low | P | Op | 2021-11-01
D-13 | Maintenance activities on manholes/carrier pipe | Fall, slips and trips and falling from height resulting in injury/death, damage to assets Engulfment, confined space access to manholes | Maintenance | Maintenance Staff | 3 | 5 | Critical | Minimise maintenance access through safety in design and design specification (material, reducing number of manholes, appropriate manhole size, access/egress etc.), confined space entry, maintenance to be competent and properly trained |  |  |  | 1 | 4 | Low | R | Op | 2021-11-01
D-14 | Unforeseen ground conditions | Damage to site and assets. Reduced system performance. | Construction | Construction Staff | 3 | 3 | Medium | Perform sufficient ground investigation along the pipe alignment. GI works procured by WSL for WSL pipeline only (excl the bridge structure and foundations etc which will be carried out by others). |  |  |  | 1 | 3 | Low | P | Client | 2021-11-01
D-15 | Contamination | Illness, infection | Construction | Construction Staff | 3 | 3 | Medium | Contractor to take samples and undertake contamination testing as required for handling and disposal |  |  |  | 3 | 3 | Medium | P | C | 2021-11-01
Add more lines above here if required
Note on K19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The Residual risk will auto-populate from the Watercare Risk Matrix table lookup after the Likelihood and Consequence levels 1-5 are selected for each

## SID Risk Register
SAFETY IN DESIGN RISK REGISTER
Project:
Project Number:
Project Design Stage:
Project Type:
Designer:
SID Review Date:
Completed By:
Checked By:
Approved By:
Revision:
RISKS ASSOCIATED WITH DESIGN ELEMENT | [7 empty] | DESIGN MITIGATION MEASURES AND RESIDUAL RISK
[5 empty] | INITIAL RISK | [6 empty] | RESIDUAL RISK
Hazard Number | Activity / Process | Hazard incl outcome Source of risk and cause / event. (Refer to Typical Hazard Prompts tab). | Stage of Work (Investigation, Construction, Operation, Commissioning, Maintenance, Demolition) | Persons Affected (Construction Staff, Maintenance Staff, Public) | Likelihood | Consequences | Initial Risk Level | Controls What Mitigations and Control Measures are already in place or have been added to the design to Reduce Risk? (Eliminate, Reduce, Inform, Control) | Further Controls What further mitigations and control measures could be considered to reduce the residual Hazards? | Barriers What are the barriers that may apply to implement these Further Controls. Why can't we do more? | Actions and Date What actions are needed to escalate and consult on the resolution of any Further Controls that have not been applied? | Likelihood | Consequences | Residual Risk Level | Information Flow For Residual Hazards (Pre-construction Stage Plan - P, Drawings - D, SID Report on Completion - R, O&M Documents - O) | Risk Owner (Designer - D, Constructor - C, Operator - Op, Owner - Ow) | Due Date Expected Date to Issue final SID Register | COMMENTS
1
2
3
4
5
6
7
8
9
10
Add more lines above here if required
Note on K19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The Residual risk will auto-populate from the Watercare Risk Matrix table lookup after the Likelihood and Consequence levels 1-5 are selected for each

## Typical Hazard Prompts
Type of Hazard
IMPORTANT NOTE: The below prompts are reminders to assist with SiD workshops, and are not an alternative to having suitably qualified personnel in attendance
Construction (incl Investigations) | Testing and Commissioning | Operations | Maintenance | Demolition | Critical Hazards
Contamination |  | Terrain / Surfaces | Maintenance access to Plant & Equipment | Heights / Depths | Working with suspended loads
Weather / Natural Hazards | Regulatory compliance | Floor surfaces to prevent slips and trips | Utilities / Services | Structural stability / premature collapse | Working around live traffic
Flooding incl working near water |  | Working near water | Confined spaces | Asbestos / Lead | Digging and working in excavations
Asbestos / Lead | Reverse flow | Visibility / Sight Lines | Working near water | Utilities / Services - including isolations | Working in confined spaces
Existing Land Use | Impurities | Barriers/Guards to plant / machinery and materials / structures | Load / Force / Energy | Demolition Sequence | Working with or in the vicinity of live energy
Previous Land Use | Instruments | Confined Spaces | Traffic/Intersections | Traffic / Intersections | Working isolated, alone or fatigued
Existing Utilities / Structures & Interfaces overhead and undergound | Services required | Traffic / Intersections | Working from a height or at depth | Traffic Management | Working with mobile plant
Wetlands, Trees, Ecology and Wildlife | Natural Hazards | Access / Egress incl exclusion zones & crossings (incl for people with disability) | Dust / Emissions / Debris | Terrain / Surfaces | Working at height
Traffic / People in vicinity | Startup / Shutdown | Manual Handling, materials, chemicals and plant and equipment | Hazardous Materials also incl production of hazardous material (such as biogas production from a Digester) | Emission of Hazardous Materials during demolition | Working with flammables or explosive or flammable areas
Traffic / Intersections | Fire / Explosion | Moving Plant & Machinery | Manual Handling, materials, chemicals and plant and equipment | Natural Hazards | Working with hazardous substances
Ground conditions | Safety equipment | Extreme Events / Evacuation | Access / Egress incl exclusion zones & crossings (incl for people with disability) | Manual Handling | Working with plant and eqiuipment
Landfill | Timing (consider staging of works and potential impact of other construction, commissioning and operationas activities) | Ergonomics | Terrain/Surfaces | Noise | Wellbeing
Temp positions of construction plant and materials | High pressure | Simplicity | Lighting including plant rooms and kiosks | Confined Space
Working from a height or at depth | Low pressure | Working from a height or at depth | Ergonomics | Load / Force / Energy
Heavy Lifting incl impact on adjacent structures | Hazardous Materials also incl production of hazardous material (such as biogas production from a Digester) | Fire / Explosion incl fire detection and fire fighting & fire tender access | Acoustic properties and noise control (eg noise isolation, insulation & absorption) | Poor visibility / night access
Manual Handling | Position / Location | Natural Hazards | Poor visibility / night access | Moving Plant & Machinery
Temporary Works | Moving Plant & Machinery | Lighting including plant rooms and kiosks | Corrosion - consider due to environment or process to take into account material selection to reduce impact (incl galvanic corrosion with dissimilar metals in contact) | Visibility / Sight Lines
Prescribed Methods / Sequence | Confined Spaces | Hazardous Materials also incl production of hazardous material (such as biogas production from a Digester) |  | Hazardous Materials also incl production of hazardous material (such as biogas production from a Digester)
Access / Egress incl exclusion zones & crossings (incl for people with disability) | Access / Egress incl exclusion zones & crossings (incl for people with disability) | HV Electrical, incl earthing, undergound and overhead cables and protection of leads and number / location of power points
Confined Spaces | HV Electrical, incl earthing, undergound and overhead cables and protection of leads and number / location of power points | LV Electrical, incl earthing, undergound and overhead cables and protection of leads and number / location of power points
Extreme Event / Evacuation | LV Electrical, incl earthing, undergound and overhead cables and protection of leads and number / location of power points | Reliability
Emergency Response | Working from a height or at depth | Traffic management
Visibility / Sight Lines | Interfaces External to the Project | Fire emergency routes and exits and fire fighting eqpt
Dust / Emissions / Debris | Utilities / Services | Site Security
Noise | Load / Force / Energy | Loading bays and ramps
Poor visibility / night access |  | Protection from chemical spills / acid burns
Sequence and timing of works |  | Acoustic properties and noise control (eg noise isolation, insulation & absorption)
Hazardous Materials also incl production of hazardous material (such as biogas production from a Digester) |  | Access to first aid rooms, incl wash rooms, showers and welfare facilities, lockers etc
Asbestos / Lead |  | Isolation - Consider if design has identified all energy sources requiring isolation and the location and number of isolation points
Electrical |  | Poor visibility / night access
Load / Force / Energy |  | Regulatory compliance
Use of scaffolding
Traffic management
Mobile crane loads on slabs
Community / public interaction - consider if there is public access to the site incl working areas and does the design consider sufficient controls to prevent harm to the public (this could include temporary works)
Excavation
Corrosion - consider due to environment or process to take into account material selection to reduce impact (incl galvanic corrosion with dissimilar metals in contact)
Movement and operation of plant and equipment

## Lookups
Stage of work | Persons Affected | Information Flow For Residual Hazards | Risk Owner | Project Type | Likelihood | Project Design Stage
Investigation | Construction Staff | P | D | Water Network | 1 | Preliminary Design
Construction | Maintenance Staff | D | C | Wastewater Network | 2 | Detailed Design
Operation | Public | R | Op | Water Treatment | 3 | Construction
Commissioning |  | O | Ow | Wastewater Treatment | 4
Maintenance |  | P,D |  |  | 5
Demolition |  | P,R
|  | P,D,R |  |  | Consequences
|  | P,D,R,O |  |  | 1
|  | D,R |  |  | 2
|  | D,R,O |  |  | 3
|  | R,O |  |  | 4
5
PLEASE DO NOT EDIT OR MOVE ANY CELLS WITH TEXT OR NUMBERS

## Risk Table
Risk Matrix Table |  |  |  | Consequences
|  |  |  | Negligible | Minor | Moderate | Severe | Extreme
|  |  |  | Injury requiring short-term first aid care and no absence from workplace | Injury requiring medical treatment and workplace absence less than 1 day | Injury requiring medical treatment or lost time of 1 day to 3 weeks | Serious injury (injuries) requiring specialist medical treatment of lost time greater than 3 weeks | Loss of life, permanent disability, or multiple serious injuries
|  |  |  | 1 | 2 | 3 | 4 | 5
Likelihood | Almost Certain | Expected to occur in most circumstances | 5 | Low | High | High | Critical | Critical
| Likely 55% to 85% | Will probably occur in most circumstances | 4 | Low | Medium | High | Critical | Critical
| Possible 30% to 55% | Likely to occur at some time | 3 | Low | Medium | Medium | High | Critical
| Unlikely 5% to 30% | More likely not occur under normal conditions | 2 | Low | Low | Medium | Medium | High
| Rare <5% | Will only occur in exceptional circumstances | 1 | Low | Low | Low | Low | High
THIS SHEET HAS BEEN LOCKED SO NO EDITING PERMITTED